## ALL
Year | ClientID | PO | MO# | ProjectDescription | ST | OT | Billing ST | Billing OT | Expenses | Total Material | PO Spent | PO%Spent | PO Left | Comp | ProjectTotalBillingEstimate | PF | Earned | Begin Date | End Date | Estimate Hours
2022 | 56213200 | 4404165949 | 4404165949-001 | 2021 Covid-19 Security Screening | 760 | 0 | 23601.6 | 0 | 0 | 0 | 23601.6 | 502.16% | -18901.6 | 0 | 4700 | 0 | 0 | 12/30/2021 | 02/28/2022 | 100
2022 | 56403200 | 56403200 | 56403200-99 | Brock Overhead Non Billable | 0 | 10 | 0 | 510.8 | 0 | 0 | 510.79 | 0.72% | 69989.19 | 0 | 70500 | 0 | 0 | 12/30/2021 | 02/28/2022 | 1500
2022 | 56403200 | 4501147751 | 3281732-21 | Remove insulation diaphragm valve | 40 | 5 | 1922.8 | 327.4 | 0 | 0 | 2250.19 | 199.48% | -1122.19 | 100 | 1128 | 0.53 | 24 | 12/30/2021 | 02/28/2022 | 24
2022 | 56403200 | 4501148137 | 3244927-21 | Re-insulate steam manual valve for TIC811/BA616 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 6.07% | 1545 | 0 | 1645 | 0 | 0 | 12/30/2021 | 02/28/2022 | 35
2022 | 56403200 | 4501160317 | 3305399-22 | Build scaffold T/R or eaplace valve | 0 | 140 | 0 | 8304 | 0 | 0 | 8304 | 830400.00% | -8304 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 24
2022 | 56403200 | 4501160317 | 3337904-22 | Build scaffold purchase nuclear level gauge L-1111 | 300 | 15 | 12777.15 | 861.05 | 0 | 0 | 13638.2 | 1363820.00% | -13638.2 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 6
2022 | 56403200 | 4501160317 | 3340338-22 | Build 2 scaffold acid line to fin needs cleaned | 0 | 240 | 0 | 14060.6 | 0 | 0 | 14060.6 | 1406060.00% | -14060.6 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 14
2022 | 56403200 | 4501160317 | 3345310-22 | Re-insulate water leak @ reactor-flu pond | 50 | 0 | 2134.3 | 0 | 0 | 130 | 2264.3 | 226430.00% | -2264.3 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 8
2022 | 56403200 | 4501160317 | 3348268-22 | Remove insulation water leak TiCI4 walkway | 190 | 0 | 8000.3 | 0 | 0 | 0 | 8000.29 | 800029.99% | -8000.29 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 36
2022 | 56403200 | 4501160317 | 3349448-22 | Build scaffold rebrick rebuild # 1 chl | 72.5 | 0 | 3177.625 | 0 | 0 | 0 | 3177.62 | 317762.50% | -3177.62 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 15
2022 | 56403200 | 4501160317 | 3349503-22 | Remove & re-insulate orival H20 leak | 100 | 0 | 4224 | 0 | 0 | 0 | 4224 | 422400.00% | -4224 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 11
2022 | 56403200 | 4501160317 | 3350623-22 | Build 2 scaffold A PRQ Coil | 65 | 25 | 2697.2 | 1595.15 | 0 | 0 | 4292.34 | 429234.99% | -4292.34 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403200 | 4501160317 | 3351042-22 | Install metal on controls package for admin HVAC | 40 | 0 | 1712.2 | 0 | 0 | 0 | 1712.2 | 171220.00% | -1712.2 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 11
2022 | 56403200 | 4501160317 | 3351552-22 | Remove insulation open H20 line for B tr. As Frozen | 462.5 | 0 | 19632.225 | 0 | 0 | 0 | 19632.22 | 1963222.49% | -19632.22 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 16
2022 | 56403200 | 4501160317 | 3351768-22 | Build scaffold hole in line to filter press feed tank | 160 | 35 | 6773.7 | 2151.65 | 0 | 0 | 8925.34 | 892534.99% | -8925.34 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403200 | 4501160317 | 3351815-022 | Build scaffold & remove and re-insulate h2o to safety showers busted | 22.5 | 0 | 923.625 | 0 | 0 | 0 | 923.62 | 92362.50% | -923.62 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 0
2022 | 56403200 | 4501160317 | 3352323-22 | Build scaffold wiper blades in A Mill | 135 | 15 | 5833.3 | 861.05 | 0 | 0 | 6694.34 | 669434.99% | -6694.34 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 15
2022 | 56403200 | 4501160317 | 3352387-22 | Build scaffold water leak northwest of #3 quench | 117.5 | 0 | 5111.575 | 0 | 0 | 0 | 5111.57 | 511157.49% | -5111.57 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 40
2022 | 56403200 | 4501160317 | 3352735-22 | Build scaffold superior for 2 crude rebuild | 65 | 50 | 2836.75 | 2989.85 | 0 | 0 | 5826.59 | 582659.99% | -5826.59 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 14
2022 | 56403200 | 4501160317 | 3352860-22 | Build scaffold electic heater A slurry room | 105 | 0 | 4536.15 | 0 | 0 | 0 | 4536.14 | 453614.99% | -4536.14 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 16
2022 | 56403200 | 4501160317 | 3353022-22 | Inpsect scaffold A Press for all A cylinders | 0 | 30 | 0 | 1816.95 | 0 | 0 | 1816.94 | 181694.99% | -1816.94 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 0
2022 | 56403200 | 4501160317 | 3353088-22 | Build scaffold all 4 cyclinders | 135 | 125 | 5887 | 7216.2 | 0 | 0 | 13103.19 | 1310319.99% | -13103.19 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 15
2022 | 56403200 | 4501160317 | 3355564-22 | Build scaffold water to ring 2 cold cyclone flow meter | 0 | 45 | 0 | 2606.2 | 0 | 0 | 2606.19 | 260619.99% | -2606.19 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403200 | 4501160317 | 3355722-22 | Build scaffold east pump PMA-5511 | 0 | 95 | 0 | 5520.4 | 0 | 0 | 5520.4 | 552040.00% | -5520.4 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 16
2022 | 56403200 | 4501160318 | 3337570-22 | Remove scaffold A Train baghouse hoist door BAG2520 | 50 | 0 | 2134.3 | 0 | 0 | 0 | 2134.29 | 213429.99% | -2134.29 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 16
2022 | 56403200 | 4501160318 | 3340805-22 | Inspect scaffold for line cooling twrs-rpr jumper line | 665 | 155 | 27980.65 | 8964.8 | 0 | 0 | 36945.45 | 3694545.00% | -36945.45 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403200 | 4501160318 | 3344280-22 | Build scaffold remove loose concrete fitl 1 thru 3 | 80 | 0 | 3374.05 | 0 | 0 | 0 | 3374.05 | 337405.00% | -3374.05 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 9
2022 | 56403200 | 4501160318 | 3345383-22 | Build scaffold 4 gas filter steam jacket | 90 | 62.5 | 3842.3 | 3675.875 | 0 | 0 | 7518.17 | 751817.49% | -7518.17 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 16
2022 | 56403200 | 4501160318 | 3349763-22 | Build scaffold 6 filter feed line | 185 | 0 | 7993.2 | 0 | 0 | 0 | 7993.19 | 799319.99% | -7993.19 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403200 | 4501160318 | 3350450-22 | Build scaffold deck drain NE of #2 RFD | 100 | 10 | 4178.55 | 658.45 | 0 | 0 | 4836.99 | 483699.99% | -4836.99 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 22
2022 | 56403200 | 4501160318 | 3350451-22 | Build scaffold deck drain by BC tank | 70 | 67.5 | 2955.3 | 3954.125 | 0 | 0 | 6909.42 | 690942.49% | -6909.42 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403200 | 4501160318 | 3351449-22 | Build scaffold #2 Gas Filter at the dome for Hydro | 430 | 125 | 17954.8 | 7216.2 | 0 | 0 | 25171 | 2517100.00% | -25171 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 0
2022 | 56403200 | 4501160318 | 3352021-22 | Build 2 scaffold space heater | 135 | 45 | 5524.55 | 2606 | 0 | 0 | 8130.54 | 813054.99% | -8130.54 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 24
2022 | 56403200 | 4501160318 | 3352022-22 | Inspect scaffold for heaters | 10 | 10 | 410.5 | 760.4 | 0 | 0 | 1170.89 | 117089.99% | -1170.89 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 0
2022 | 56403200 | 4501160318 | 3352665-22 | Build scaffold caustic line PMA-2156 | 222.5 | 677.5 | 9396.375 | 38649.725 | 0 | 0 | 48046.09 | 4804609.99% | -48046.09 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 18
2022 | 56403200 | 4501160318 | 3353001-22 | Build scaffold tremporary closure aroung #7 filt | 202.5 | 50 | 8591.875 | 2895 | 0 | 0 | 11486.87 | 1148687.49% | -11486.87 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 20
2022 | 56403200 | 4501160318 | 3353572-22 | Remove & re-insulate water leak above B 150 station | 0 | 110 | 0 | 6589 | 0 | 0 | 6588.99 | 658899.99% | -6588.99 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 0
2022 | 56403200 | 4501160318 | 3353904-22 | Build scaffold #1 blend tank | 127.5 | 0 | 5422.225 | 0 | 0 | 0 | 5422.22 | 542222.49% | -5422.22 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403200 | 4501160318 | 3353981-22 | Build scaffold & remove & re-insulate 12' CW piping | 80 | 5 | 3374.05 | 278.25 | 0 | 0 | 3652.29 | 365229.99% | -3652.29 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 24
2022 | 56403200 | 4501160318 | 3354093-22 | Build scaffold #2 MZR feed bin live bottom boot | 0 | 85 | 0 | 5046.65 | 0 | 0 | 5046.65 | 504665.00% | -5046.65 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403200 | 4501160318 | 3354291-22 | Build scaffold steam jacket leak on 2 gas filter | 80 | 15 | 3444.25 | 811.9 | 0 | 0 | 4256.15 | 425615.00% | -4256.15 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 16
2022 | 56403200 | 4501160318 | 3354448-22 | Build 3 scaffold FLT-2331 filter #3 rotary | 195 | 137.5 | 8066 | 7774.925 | 0 | 0 | 15840.92 | 1584092.49% | -15840.92 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 36
2022 | 56403200 | 4501160318 | 3355138-22 | Build scaffold water libe to A trn | 50 | 0 | 2089.7 | 0 | 0 | 0 | 2089.7 | 208970.00% | -2089.7 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403200 | 4501160319 | 3346655-22 | Build scaffold change FV-9586 acturator | 262.5 | 20 | 11141.575 | 1271.2 | 0 | 0 | 12412.77 | 1241277.50% | -12412.77 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 10
2022 | 56403200 | 4501160319 | 3347771-22 | Re-insulate gages/breaches | 80 | 0 | 3502 | 0 | 0 | 0 | 3501.99 | 620.92% | -2937.99 | 0 | 564 | 0 | 0 | 02/11/2022 | 04/11/2022 | 12
2022 | 56403200 | 4501160319 | 3348700-22 | Build scaffold vent piping off FA-448 | 77.5 | 30 | 3329.175 | 1767.8 | 0 | 0 | 5096.97 | 509697.50% | -5096.97 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 24
2022 | 56403200 | 4501160319 | 3349969-22 | Build scaffold GA-722A | 312.5 | 50 | 13288.25 | 3190.3 | 0 | 0 | 16478.55 | 1647855.00% | -16478.55 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 18
2022 | 56403200 | 4501160319 | 3350511-22 | Re-insulate pump GA-724B | 285 | 0 | 11987.45 | 0 | 0 | 0 | 11987.45 | 1198745.00% | -11987.45 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 28
2022 | 56403200 | 4501160319 | 3351375-22 | Build scaffold PA-780 (CB-703 Stack Seal) | 125 | 45 | 5455.8 | 2435.7 | 0 | 0 | 7891.49 | 789149.99% | -7891.49 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 13
2022 | 56403200 | 4501160319 | 3352519-22 | Build scaffold 3'' chain valve | 162.5 | 15 | 6966.225 | 811.9 | 0 | 0 | 7778.12 | 777812.49% | -7778.12 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403200 | 4501160319 | 3352651-22 | Build scaffold sfaety shower water line froze | 300 | 0 | 12548.8 | 0 | 0 | 0 | 12548.8 | 1254880.00% | -12548.8 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 24
2022 | 56403200 | 4501160319 | 3352761-22 | Build scaffold ore line leaking | 462.5 | 140 | 19280.325 | 8016 | 0 | 0 | 27296.32 | 2729632.50% | -27296.32 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 0
2022 | 56403200 | 4501160319 | 3352918-22 | Re-insulate for rebuild reboiler EA701A | 65 | 0 | 2836.75 | 0 | 0 | 0 | 2836.75 | 283675.00% | -2836.75 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 14
2022 | 56403200 | 4501160319 | 3353114-22 | Re-insulate water line broken FG-790 | 95 | 0 | 4040.15 | 0 | 0 | 0 | 4040.15 | 404015.00% | -4040.15 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 12
2022 | 56403200 | 4501160319 | 3353647-22 | Build scaffold DA-780 Tower | 380 | 70 | 16066.6 | 3849.8 | 0 | 0 | 19916.39 | 1991639.99% | -19916.39 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 20
2022 | 56403200 | 4501160320 | 3306764-22 | Build scaffold FD-509B Tank media | 315 | 180 | 13230.55 | 10654.6 | 0 | 0 | 23885.15 | 2388515.00% | -23885.15 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 32
2022 | 56403200 | 4501160320 | 3336593-22 | Build scaffold abandoned material PA-847 | 132.5 | 0 | 5582.875 | 0 | 0 | 0 | 5582.87 | 558287.49% | -5582.87 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 26
2022 | 56403200 | 4501160320 | 3343831-22 | Re-insulatet 3 scaffold on slurry line on Fg6/7 | 0 | 0 | 0 | 0 | 0 | 430 | 430 | 43000.00% | -430 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 20
2022 | 56403200 | 4501160320 | 3352088-22 | Re-insulation blankets on water line | 100 | 0 | 4113.4 | 0 | 0 | 0 | 4113.4 | 411340.00% | -4113.4 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 10
2022 | 56403200 | 4501160320 | 3352517-22 | Re-insulate coming slurry line | 145 | 0 | 6240.45 | 0 | 0 | 0 | 6240.45 | 624045.00% | -6240.45 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 8
2022 | 56403200 | 4501160320 | 3352635-22 | Remove and re-insulate valve suspect | 180 | 0 | 7825 | 0 | 0 | 0 | 7824.99 | 782499.99% | -7824.99 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 10
2022 | 56403200 | 4501160320 | 3353396-22 | Remove insulation new tunnel | 87.5 | 0 | 3699.275 | 0 | 0 | 0 | 3699.27 | 369927.50% | -3699.27 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 10
2022 | 56403200 | 4501160320 | 3353398-22 | Re-insulate false load line | 180 | 0 | 7677.2 | 0 | 0 | 0 | 7677.19 | 767719.99% | -7677.19 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 24
2022 | 56403200 | 4501160320 | 3353999-22 | Remove & re-insulate steam line | 135 | 0 | 5747.45 | 0 | 0 | 0 | 5747.45 | 574745.00% | -5747.45 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 20
2022 | 56403200 | 4501160320 | 3354079-22 | Build scaffold EA-810 Bypass valve replacement | 110 | 0 | 4733.5 | 0 | 0 | 0 | 4733.49 | 473349.99% | -4733.49 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 0
2022 | 56403200 | 4501160320 | 3354509-22 | Build 2 scaffold remove pieces from inside vat | 90 | 30 | 3854.75 | 1899.7 | 0 | 0 | 5754.44 | 575444.99% | -5754.44 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403200 | 4501160320 | 3355053-22 | Build scaffold relocate transmitter L-6285 | 70 | 0 | 2971.8 | 0 | 0 | 0 | 2971.79 | 297179.99% | -2971.79 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 14
2022 | 56403300 | 4501160317 | 3303963-22 | Build scaffold startup Srubb | 60 | 20 | 2413.5 | 1520.8 | 0 | 0 | 3934.3 | 393430.00% | -3934.3 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 16
2022 | 56403300 | 4501160317 | 3333856-22 | Build had barricade #2 rebuild vessel # 2 Chl | 15 | 0 | 591 | 0 | 0 | 0 | 590.99 | 59099.99% | -590.99 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 6
2022 | 56403300 | 4501160317 | 3333857-22 | Build scaffold #2 rebuild piping/valves | 505 | 30 | 21250.85 | 1922.55 | 0 | 0 | 23173.4 | 2317340.00% | -23173.4 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 16
2022 | 56403300 | 4501160317 | 3335428-22 | remove scaffold for RG-009 | 55 | 0 | 2405.55 | 0 | 0 | 0 | 2405.55 | 240555.00% | -2405.55 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 6
2022 | 56403300 | 4501160317 | 3342771-22 | Builld scaffold B HCL line to AWD | 380 | 325 | 15506.85 | 18518.4 | 0 | 0 | 34025.25 | 3402525.00% | -34025.25 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 16
2022 | 56403300 | 4501160317 | 3346060-22 | Build 7 scaffold for I&E | 37.5 | 1045 | 1539.375 | 60078.225 | 0 | 0 | 61617.59 | 6161759.99% | -61617.59 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 30
2022 | 56403300 | 4501160317 | 3348258-22 | Build hard barricade set up wash # 2 crude | 72.5 | 0 | 3136.375 | 0 | 0 | 0 | 3136.37 | 313637.49% | -3136.37 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 18
2022 | 56403300 | 4501160317 | 3348946-22 | Remove scaffold chute leak A elev | 0 | 60 | 0 | 3293.3 | 0 | 0 | 3293.29 | 329329.99% | -3293.29 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 20
2022 | 56403300 | 4501160317 | 3349518-22 | Inspect 5 scaffold for swing #3 Chlorinator to B-Train | 220 | 0 | 8985 | 0 | 0 | 227.5 | 9212.49 | 560.03% | -7567.49 | 0 | 1645 | 0 | 0 | 02/02/2022 | 04/02/2022 | 35
2022 | 56403300 | 4501160317 | 3349851-22 | Build scaffold mist eliminator MEL-1212 | 350 | 175 | 14885.3 | 10292.45 | 0 | 0 | 25177.75 | 2517775.00% | -25177.75 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 89
2022 | 56403300 | 4501160317 | 3349997-22 | Build scaffold SR Southeast spiral cooler | 120 | 40 | 5061.5 | 2180.3 | 0 | 0 | 7241.79 | 724179.99% | -7241.79 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 20
2022 | 56403300 | 4501160317 | 3350627-22 | Build scaffold A Fume disposal for cleaning | 65 | 45 | 2774.8 | 2757.3 | 0 | 0 | 5532.09 | 553209.99% | -5532.09 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 12
2022 | 56403300 | 4501160317 | 3350650-22 | Build Hard scaffold pump bad | 0 | 120 | 0 | 6994.4 | 0 | 0 | 6994.4 | 699440.00% | -6994.4 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 12
2022 | 56403300 | 4501160317 | 3351257-22 | Build scaffold slurry tank nozzle | 70 | 100 | 3050.25 | 5624.5 | 0 | 0 | 8674.74 | 867474.99% | -8674.74 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 9
2022 | 56403300 | 4501160317 | 3351815-22 | Build scaffold & remove and re-insulate h2o to safety showers busted | 90 | 30 | 3854.75 | 1873.4 | 0 | 0 | 5728.14 | 572814.99% | -5728.14 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 20
2022 | 56403300 | 4501160317 | 3352099-22 | Build scaffold t/r b press mouse | 70 | 0 | 3050.25 | 0 | 0 | 0 | 3050.25 | 305025.00% | -3050.25 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 14
2022 | 56403300 | 4501160317 | 3352418-22 | Remove &re-insulate measure fab line 6 surege | 55 | 0 | 2327.95 | 0 | 0 | 0 | 2327.95 | 232795.00% | -2327.95 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 9
2022 | 56403300 | 4501160317 | 3352514-22 | Re-insulate H20 line at NaOH makeup | 62.5 | 0 | 2635.825 | 0 | 0 | 0 | 2635.82 | 263582.50% | -2635.82 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 10
2022 | 56403300 | 4501160317 | 3353395-22 | Build scaffold swing A Train to #2 CHL march 22' | 70 | 20 | 2971.8 | 1116.45 | 0 | 0 | 4088.24 | 408824.99% | -4088.24 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 9
2022 | 56403300 | 4501160317 | 3353529-22 | Re-insulate water leak first deck chlor | 30 | 0 | 1301.7 | 0 | 0 | 0 | 1301.69 | 130169.99% | -1301.69 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 10
2022 | 56403300 | 4501160317 | 3353612-22 | Build scaffold water leaks as needed | 100 | 75 | 4257 | 4472.3 | 0 | 0 | 8729.29 | 872929.99% | -8729.29 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 18
2022 | 56403300 | 4501160317 | 3353654-22 | Remove & re-insulate CHL #2 CL-025 | 65 | 0 | 2836.75 | 0 | 0 | 0 | 2836.75 | 283675.00% | -2836.75 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 15
2022 | 56403300 | 4501160317 | 3353683-22 | Build & remove scaffold butterfly valve is brocken | 180 | 0 | 7606.3 | 0 | 0 | 0 | 7606.29 | 760629.99% | -7606.29 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 20
2022 | 56403300 | 4501160317 | 3354679-22 | Build & remove new ganway #1 carspot | 55 | 0 | 2278.45 | 0 | 0 | 0 | 2278.45 | 227845.00% | -2278.45 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 11
2022 | 56403300 | 4501160317 | 3354683-22 | Build scaffold at waste tanks | 190 | 100 | 8033.3 | 5881.4 | 0 | 0 | 13914.69 | 1391469.99% | -13914.69 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 0
2022 | 56403300 | 4501160317 | 3354712-22 | Inspect scaffold for #5 & #6 surge TNK | 0 | 20 | 0 | 1211.3 | 0 | 0 | 1211.29 | 121130.00% | -1211.29 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 0
2022 | 56403300 | 4501160318 | 3310516-22 | build 2 scaffold and re-insulate for #6 Mizrocnizer Discharge piping | 205 | 0 | 9069.25 | 0 | 0 | 0 | 9069.25 | 906925.00% | -9069.25 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 12
2022 | 56403300 | 4501160318 | 3347600-22 | Build scaffold to hard barricade east end | 90 | 0 | 3972 | 0 | 0 | 0 | 3972 | 397200.00% | -3972 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 0
2022 | 56403300 | 4501160318 | 3349769-22 | Build scaffold offgas pipe cleaning # 2 MZR | 50 | 35 | 2056.7 | 2026.65 | 0 | 0 | 4083.35 | 408335.00% | -4083.35 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 10
2022 | 56403300 | 4501160318 | 3349912-22 | Build 2 scaffold boot was hole on south east side of cone | 165 | 0 | 7027.75 | 0 | 0 | 0 | 7027.74 | 747.63% | -6087.74 | 0 | 940 | 0 | 0 | 02/11/2022 | 04/11/2022 | 20
2022 | 56403300 | 4501160318 | 3350970-22 | Build scaffold #5 gas filter rundownleg | 575 | 0 | 24568.75 | 0 | 0 | 0 | 24568.75 | 2456875.00% | -24568.75 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 20
2022 | 56403300 | 4501160318 | 3352665-22 | Build scaffold caustic line PMA-2156 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 10000.00% | -100 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 18
2022 | 56403300 | 4501160318 | 3352700-22 | Build scaffold & remove insulate to find/repair leaks | 167.5 | 40 | 7064.225 | 2429.9 | 0 | 0 | 9494.12 | 949412.49% | -9494.12 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 20
2022 | 56403300 | 4501160318 | 3353334-22 | Build 3 scaffold & remove and re-insulate city water pipe | 575 | 80 | 24182.95 | 4606.55 | 0 | 0 | 28789.5 | 2878950.00% | -28789.5 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 32
2022 | 56403300 | 4501160318 | 3353902-22 | Remove & re-insulate water line | 132.5 | 5 | 5455.775 | 278.25 | 0 | 0 | 5734.02 | 573402.49% | -5734.02 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 24
2022 | 56403300 | 4501160318 | 3354065-22 | Build scaffold for paire hoist inspect | 365 | 0 | 15313.75 | 0 | 0 | 0 | 15313.74 | 1531374.99% | -15313.74 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 56
2022 | 56403300 | 4501160318 | 3354436-22 | Build scaffold hydro run pipinh from gas filter to BC | 80 | 20 | 3444.25 | 1188.45 | 0 | 0 | 4632.69 | 463269.99% | -4632.69 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 16
2022 | 56403300 | 4501160318 | 3354574-22 | Build scaffold change boot #2 GF live bottom | 50 | 0 | 2089.7 | 0 | 0 | 0 | 2089.7 | 208970.00% | -2089.7 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 10
2022 | 56403300 | 4501160318 | 3355031-22 | Build scaffold agiator blades | 50 | 5 | 2167.3 | 278.25 | 0 | 0 | 2445.55 | 244555.00% | -2445.55 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 12
2022 | 56403300 | 4501160318 | 3355285-22 | Build scaffold city water line leak | 85 | 25 | 3587.55 | 1470.35 | 0 | 0 | 5057.89 | 505789.99% | -5057.89 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 12
2022 | 56403300 | 4501160319 | 3345137-22 | Build scaffold vent line from A & B train | 70 | 0 | 2971.8 | 0 | 0 | 0 | 2971.8 | 297180.00% | -2971.8 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 12
2022 | 56403300 | 4501160319 | 3345406-22 | Build scaffold chlorine vaporization | 62.5 | 0 | 2635.825 | 0 | 0 | 0 | 2635.82 | 263582.49% | -2635.82 | 0 | 0 | 0 | 0 | 03/07/2022 | 05/07/2022 | 24
2022 | 56403300 | 4501160319 | 3348154-22 | Re-insulate fab up new spool DA-780 to FA-782 | 145 | 30 | 6022.45 | 1767.8 | 0 | 0 | 7790.25 | 779025.00% | -7790.25 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 6
2022 | 56403300 | 4501160319 | 3348784-22 | Remove & re-insulate FI-2707 to mag flowmeter | 127.5 | 0 | 5522.075 | 0 | 0 | 0 | 5522.07 | 552207.49% | -5522.07 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 16
2022 | 56403300 | 4501160319 | 3350455-22 | Inspect scaffold #9 Ore conveying leak | 0 | 5 | 0 | 255.4 | 0 | 0 | 255.4 | 25540.00% | -255.4 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 0
2022 | 56403300 | 4501160319 | 3350803-22 | Re-insulate main steam line for EA-102 | 200 | 0 | 8716.2 | 0 | 0 | 0 | 8716.19 | 871619.99% | -8716.19 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 28
2022 | 56403300 | 4501160319 | 3350905-22 | Remove and re-insulate vent stack for EA-701 | 127.5 | 0 | 5374.275 | 0 | 0 | 0 | 5374.27 | 537427.49% | -5374.27 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 10
2022 | 56403300 | 4501160319 | 3351624-22 | Re-insulate 2 lime block valves | 70 | 0 | 2943.7 | 0 | 0 | 0 | 2943.69 | 294369.99% | -2943.69 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403300 | 4501160319 | 3351685-22 | Re-insulate D2 line | 200 | 0 | 8382 | 0 | 0 | 0 | 8381.99 | 838199.99% | -8381.99 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 18
2022 | 56403300 | 4501160319 | 3352659-22 | Re-insulate water line broken 2nd deck of cond | 122.5 | 0 | 5169.025 | 0 | 0 | 0 | 5169.02 | 516902.49% | -5169.02 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 16
2022 | 56403300 | 4501160320 | 3214328-22 | Build scaffold for 42A Draft TNK | 5 | 55 | 205.25 | 3162.5 | 0 | 0 | 3367.74 | 298.55% | -2239.74 | 0 | 1128 | 0 | 0 | 02/02/2022 | 04/02/2022 | 24
2022 | 56403300 | 4501160320 | 3343831-22 | Re-insulatet 3 scaffold on slurry line on Fg6/7 | 30 | 0 | 1198.5 | 0 | 0 | 0 | 1198.5 | 119850.00% | -1198.5 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 20
2022 | 56403300 | 4501160320 | 3347759-22 | Remove scaffold equip drain & beam | 62.5 | 0 | 2655.675 | 0 | 0 | 0 | 2655.67 | 265567.50% | -2655.67 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 15
2022 | 56403300 | 4501160320 | 3348529-22 | Build scaffold EF-003 C.T. | 157.5 | 0 | 6501.875 | 0 | 0 | 0 | 6501.87 | 650187.49% | -6501.87 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 20
2022 | 56403300 | 4501160320 | 3348632-22 | Remove scaffold floor drain | 62.5 | 0 | 2655.675 | 0 | 0 | 0 | 2655.67 | 265567.50% | -2655.67 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 12
2022 | 56403300 | 4501160320 | 3349608-22 | Re-insulate disconnect old CI2 line | 115 | 0 | 4959.45 | 0 | 0 | 0 | 4959.44 | 495944.99% | -4959.44 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 10
2022 | 56403300 | 4501160320 | 3351481-22 | Build scaffold expansion joint on GA-611 | 77.5 | 0 | 3254.925 | 0 | 0 | 0 | 3254.92 | 325492.50% | -3254.92 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 16
2022 | 56403300 | 4501160320 | 3351972-22 | Inpect scaffold pipe suppoet above FA-640 | 0 | 5 | 0 | 380.2 | 0 | 0 | 380.2 | 38020.00% | -380.2 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 0
2022 | 56403300 | 4501160320 | 3352446-22 | Build scaffold in fininshing | 0 | 50 | 0 | 2940.7 | 0 | 0 | 2940.69 | 294069.99% | -2940.69 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 16
2022 | 56403300 | 4501160320 | 3353054-22 | Re-insulate bare line at lab sump | 0 | 30 | 0 | 1873.4 | 0 | 0 | 1873.4 | 187340.00% | -1873.4 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 6
2022 | 56403300 | 4501160320 | 3354166-22 | Remove insulate check valve BA-616 | 32.5 | 0 | 1379.575 | 0 | 0 | 0 | 1379.57 | 137957.50% | -1379.57 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 12
2022 | 56403300 | 4501160320 | 3354305-22 | Build scaffold steam line | 175 | 0 | 7562 | 0 | 0 | 0 | 7561.99 | 756199.99% | -7561.99 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 50
2022 | 56403300 | 4501160320 | 3354564-22 | Build scaffold FD-509A bleed valve | 90 | 0 | 3776.3 | 0 | 0 | 0 | 3776.29 | 377629.99% | -3776.29 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 0
2022 | 56403300 | 4501160320 | 3355174-22 | Remove insulate piece | 40 | 0 | 1712.2 | 0 | 0 | 0 | 1712.19 | 171219.99% | -1712.19 | 0 | 0 | 0 | 0 | 10/10/2022 | 12/10/2022 | 8
2022 | 56403300 | 4501160320 | 3355307-22 | Build scaffold agitator fell off into tank | 40 | 0 | 1756.8 | 0 | 0 | 0 | 1756.8 | 175680.00% | -1756.8 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 12
2022 | 56403600 | 56403600 | 56403600-99 | Brock Overhead Non Billable | 0 | 240 | 0 | 10504.8 | 0 | 0 | 10504.79 | 1050479.99% | -10504.79 | 0 | 0 | 0 | 0 | 03/21/2022 | 05/21/2022 | 200
2022 | 56500300 | 4404591689 | 4404591689-001 | Build/remove Scaffold For Line 1 Mixer | 0 | 150 | 0 | 8822.1 | 0 | 0 | 8822.1 | 234.63% | -5062.1 | 0 | 3760 | 0 | 0 | 02/11/2022 | 04/11/2022 | 80

## ALLBarriers
Year | ClientID | Month | MonthN | CLASS | ST Hours | OT Hours | TotalHours | ST Cost | OT Cost
2022 | 56403200 | 1 | January | LMI-PD | 2 | 0 | 2 | 82.1 | 0
2022 | 56403200 | 1 | January | LMI-SD | 1 | 0 | 1 | 41.05 | 0
2022 | 56403200 | 1 | January | LMI-TM | 2 | 0 | 2 | 82.1 | 0
2022 | 56403300 | 1 | January | LMS-MD | 3.5 | 0 | 3.5 | 143.675 | 0
2022 | 56403300 | 1 | January | LMS-PD | 5 | 1 | 6 | 205.25 | 55.65
2022 | 56403300 | 1 | January | LMS-SD | 2.5 | 0.5 | 3 | 102.625 | 27.825
2022 | 56403300 | 1 | January | LMS-TB | 4 | 0 | 4 | 164.2 | 0
2022 | 56403300 | 1 | January | LMS-TM | 6 | 0 | 6 | 246.3 | 0
2022 | 56403300 | 1 | January | LMSB-MD | 1.25 | 0 | 1.25 | 47.1875 | 0
2022 | 56403300 | 1 | January | LMSB-PD | 1.5 | 0.5 | 2 | 56.625 | 25.54
2022 | 56403300 | 1 | January | LMSB-SD | 0.75 | 0.25 | 1 | 28.3125 | 12.77
2022 | 56403300 | 1 | January | LMSB-TB | 1 | 0 | 1 | 37.75 | 0
2022 | 56403300 | 1 | January | LMSB-TM | 2 | 0 | 2 | 75.5 | 0
2022 | 56403200 | 2 | February | LMI-CD | 4.5 | 0 | 4.5 | 184.725 | 0
2022 | 56403200 | 2 | February | LMI-FS | 83.25 | 0.5 | 83.75 | 3417.4125 | 27.825
2022 | 56403300 | 2 | February | LMI-FS | 3 | 0 | 3 | 123.15 | 0
2022 | 56403300 | 2 | February | LMI-MD | 1.5 | 0 | 1.5 | 61.575 | 0
2022 | 56403200 | 2 | February | LMI-MD | 27 | 2 | 29 | 1108.35 | 111.3
2022 | 56403200 | 2 | February | LMI-ML | 2 | 0 | 2 | 82.1 | 0
2022 | 56403200 | 2 | February | LMI-MT | 0 | 2 | 2 | 0 | 111.3
2022 | 56403200 | 2 | February | LMI-OD | 2.25 | 0 | 2.25 | 92.3625 | 0
2022 | 56403300 | 2 | February | LMI-OD | 1.5 | 0 | 1.5 | 61.575 | 0
2022 | 56403300 | 2 | February | LMI-PD | 2 | 0 | 2 | 82.1 | 0
2022 | 56403200 | 2 | February | LMI-PD | 56.25 | 3.5 | 59.75 | 2309.0625 | 194.775
2022 | 56403200 | 2 | February | LMI-SD | 25.75 | 2.25 | 28 | 1057.0375 | 125.2125
2022 | 56403300 | 2 | February | LMI-SD | 1 | 0 | 1 | 41.05 | 0
2022 | 56403300 | 2 | February | LMI-TB | 2 | 0 | 2 | 82.1 | 0
2022 | 56403200 | 2 | February | LMI-TB | 24.5 | 0 | 24.5 | 1005.725 | 0
2022 | 56403200 | 2 | February | LMI-TM | 49.5 | 2.5 | 52 | 2031.975 | 139.125
2022 | 56403300 | 2 | February | LMI-TM | 2 | 0 | 2 | 82.1 | 0
2022 | 56403200 | 2 | February | LMI-YW | 0.5 | 0 | 0.5 | 20.525 | 0
2022 | 56403200 | 2 | February | LMIB-CD | 0.75 | 0 | 0.75 | 28.3125 | 0
2022 | 56403200 | 2 | February | LMIB-FS | 10.5 | 0 | 10.5 | 396.375 | 0
2022 | 56403200 | 2 | February | LMIB-MD | 2 | 0.25 | 2.25 | 75.5 | 12.77
2022 | 56403200 | 2 | February | LMIB-MT | 0 | 1 | 1 | 0 | 51.08
2022 | 56403200 | 2 | February | LMIB-PD | 6.75 | 0.5 | 7.25 | 254.8125 | 25.54
2022 | 56403200 | 2 | February | LMIB-SD | 3.25 | 0.25 | 3.5 | 122.6875 | 12.77
2022 | 56403200 | 2 | February | LMIB-TB | 3 | 0 | 3 | 113.25 | 0
2022 | 56403200 | 2 | February | LMIB-TM | 6.75 | 0.25 | 7 | 254.8125 | 12.77
2022 | 56403200 | 2 | February | LMIB-YW | 0.5 | 0 | 0.5 | 18.875 | 0
2022 | 56403300 | 2 | February | LMS-BT | 1 | 0 | 1 | 41.05 | 0
2022 | 56403300 | 2 | February | LMS-FS | 4 | 0 | 4 | 164.2 | 0
2022 | 56403300 | 2 | February | LMS-KD | 19.25 | 0 | 19.25 | 790.2125 | 0
2022 | 56403300 | 2 | February | LMS-LO | 3 | 0 | 3 | 123.15 | 0
2022 | 56403300 | 2 | February | LMS-MD | 41.25 | 6.75 | 48 | 1693.3125 | 375.6375
2022 | 56403200 | 2 | February | LMS-MD | 0.5 | 0 | 0.5 | 20.525 | 0
2022 | 56403300 | 2 | February | LMS-OD | 9 | 0 | 9 | 369.45 | 0
2022 | 56403300 | 2 | February | LMS-PD | 96 | 47.25 | 143.25 | 3940.8 | 2629.4625
2022 | 56403200 | 2 | February | LMS-PD | 1 | 0 | 1 | 41.05 | 0
2022 | 56500300 | 2 | February | LMS-PD | 0 | 0.75 | 0.75 | 0 | 41.7375
2022 | 56403300 | 2 | February | LMS-SC | 2.5 | 0 | 2.5 | 102.625 | 0
2022 | 56403300 | 2 | February | LMS-SD | 48 | 24.5 | 72.5 | 1970.4 | 1363.425
2022 | 56500300 | 2 | February | LMS-SD | 0 | 0.75 | 0.75 | 0 | 41.7375
2022 | 56403200 | 2 | February | LMS-SD | 0.5 | 0 | 0.5 | 20.525 | 0
2022 | 56403300 | 2 | February | LMS-SM | 1 | 0 | 1 | 41.05 | 0
2022 | 56403300 | 2 | February | LMS-TB | 48 | 12 | 60 | 1970.4 | 667.8
2022 | 56403200 | 2 | February | LMS-TB | 1 | 0 | 1 | 41.05 | 0
2022 | 56403200 | 2 | February | LMS-TM | 0.5 | 0 | 0.5 | 20.525 | 0
2022 | 56500300 | 2 | February | LMS-TM | 0 | 6 | 6 | 0 | 333.9
2022 | 56403300 | 2 | February | LMS-TM | 85 | 24.5 | 109.5 | 3489.25 | 1363.425
2022 | 56403300 | 2 | February | LMS-WD | 15 | 1.5 | 16.5 | 615.75 | 83.475
2022 | 56403300 | 2 | February | LMS-YW | 35.75 | 48.25 | 84 | 1467.5375 | 2685.1125
2022 | 56500300 | 2 | February | LMS-YW | 0 | 1.5 | 1.5 | 0 | 83.475
2022 | 56403300 | 2 | February | LMSB-FS | 1.25 | 0 | 1.25 | 47.1875 | 0
2022 | 56403300 | 2 | February | LMSB-KD | 5.75 | 0 | 5.75 | 217.0625 | 0
2022 | 56403300 | 2 | February | LMSB-LO | 1 | 0 | 1 | 37.75 | 0
2022 | 56403300 | 2 | February | LMSB-MD | 14 | 2.5 | 16.5 | 528.5 | 127.7
2022 | 56403300 | 2 | February | LMSB-OD | 3 | 0 | 3 | 113.25 | 0
2022 | 56403300 | 2 | February | LMSB-PD | 30.5 | 13 | 43.5 | 1151.375 | 664.04
2022 | 56500300 | 2 | February | LMSB-PD | 0 | 0.25 | 0.25 | 0 | 12.77
2022 | 56403300 | 2 | February | LMSB-SC | 0.5 | 0 | 0.5 | 18.875 | 0
2022 | 56403300 | 2 | February | LMSB-SD | 15.75 | 6.75 | 22.5 | 594.5625 | 344.79
2022 | 56500300 | 2 | February | LMSB-SD | 0 | 0.25 | 0.25 | 0 | 12.77
2022 | 56403300 | 2 | February | LMSB-SM | 0.5 | 0 | 0.5 | 18.875 | 0
2022 | 56403300 | 2 | February | LMSB-TB | 16.5 | 3.5 | 20 | 622.875 | 178.78
2022 | 56403300 | 2 | February | LMSB-TM | 27.25 | 7.5 | 34.75 | 1028.6875 | 383.1
2022 | 56500300 | 2 | February | LMSB-TM | 0 | 2 | 2 | 0 | 102.16
2022 | 56403300 | 2 | February | LMSB-WD | 7 | 0.5 | 7.5 | 264.25 | 25.54
2022 | 56403300 | 2 | February | LMSB-YW | 12 | 15 | 27 | 453 | 766.2
2022 | 56500300 | 2 | February | LMSB-YW | 0 | 0.5 | 0.5 | 0 | 25.54
2022 | 56403200 | 3 | March | LMI-FS | 34 | 0 | 34 | 1395.7 | 0
2022 | 56403300 | 3 | March | LMI-FS | 10 | 0 | 10 | 410.5 | 0
2022 | 56403300 | 3 | March | LMI-MD | 2 | 0 | 2 | 82.1 | 0
2022 | 56403200 | 3 | March | LMI-MD | 10 | 0 | 10 | 410.5 | 0
2022 | 56403200 | 3 | March | LMI-ML | 1.5 | 0 | 1.5 | 61.575 | 0
2022 | 56403200 | 3 | March | LMI-PD | 20.5 | 0 | 20.5 | 841.525 | 0
2022 | 56403300 | 3 | March | LMI-PD | 4 | 0 | 4 | 164.2 | 0
2022 | 56403300 | 3 | March | LMI-SD | 2 | 0 | 2 | 82.1 | 0
2022 | 56403200 | 3 | March | LMI-SD | 10.25 | 0 | 10.25 | 420.7625 | 0
2022 | 56403200 | 3 | March | LMI-TB | 9 | 0 | 9 | 369.45 | 0
2022 | 56403300 | 3 | March | LMI-TB | 2.5 | 0 | 2.5 | 102.625 | 0
2022 | 56403300 | 3 | March | LMI-TM | 6.5 | 0 | 6.5 | 266.825 | 0
2022 | 56403200 | 3 | March | LMI-TM | 20.75 | 0 | 20.75 | 851.7875 | 0
2022 | 56403200 | 3 | March | LMIB-FS | 1 | 0 | 1 | 37.75 | 0
2022 | 56403300 | 3 | March | LMIB-FS | 2 | 0 | 2 | 75.5 | 0
2022 | 56403300 | 3 | March | LMIB-MD | 0.5 | 0 | 0.5 | 18.875 | 0
2022 | 56403200 | 3 | March | LMIB-MD | 1 | 0 | 1 | 37.75 | 0
2022 | 56403200 | 3 | March | LMIB-PD | 4 | 0 | 4 | 151 | 0
2022 | 56403300 | 3 | March | LMIB-PD | 1 | 0 | 1 | 37.75 | 0
2022 | 56403300 | 3 | March | LMIB-SD | 0.5 | 0 | 0.5 | 18.875 | 0
2022 | 56403200 | 3 | March | LMIB-SD | 2 | 0 | 2 | 75.5 | 0
2022 | 56403200 | 3 | March | LMIB-TB | 1.5 | 0 | 1.5 | 56.625 | 0
2022 | 56403300 | 3 | March | LMIB-TB | 0.5 | 0 | 0.5 | 18.875 | 0
2022 | 56403300 | 3 | March | LMIB-TM | 1.5 | 0 | 1.5 | 56.625 | 0
2022 | 56403200 | 3 | March | LMIB-TM | 3 | 0 | 3 | 113.25 | 0
2022 | 56403300 | 3 | March | LMS-FS | 21.25 | 8.25 | 29.5 | 872.3125 | 459.1125
2022 | 56403300 | 3 | March | LMS-KD | 6.25 | 0 | 6.25 | 256.5625 | 0
2022 | 56403300 | 3 | March | LMS-LO | 5.25 | 0 | 5.25 | 215.5125 | 0
2022 | 56403300 | 3 | March | LMS-MD | 44.5 | 6 | 50.5 | 1826.725 | 333.9
2022 | 56403300 | 3 | March | LMS-OD | 10 | 0 | 10 | 410.5 | 0
2022 | 56403300 | 3 | March | LMS-PD | 89.75 | 53.5 | 143.25 | 3684.2375 | 2977.275
2022 | 56403300 | 3 | March | LMS-SD | 45.25 | 28 | 73.25 | 1857.5125 | 1558.2
2022 | 56403300 | 3 | March | LMS-TB | 44.5 | 6.25 | 50.75 | 1826.725 | 347.8125
2022 | 56403300 | 3 | March | LMS-TM | 81 | 24.75 | 105.75 | 3325.05 | 1377.3375
2022 | 56403300 | 3 | March | LMS-WD | 0.75 | 0 | 0.75 | 30.7875 | 0
2022 | 56403300 | 3 | March | LMS-YW | 18.25 | 14 | 32.25 | 749.1625 | 779.1
2022 | 56403300 | 3 | March | LMSB-FS | 0 | 2.75 | 2.75 | 0 | 140.47
2022 | 56403300 | 3 | March | LMSB-KD | 1.75 | 0 | 1.75 | 66.0625 | 0
2022 | 56403300 | 3 | March | LMSB-LO | 1.75 | 0 | 1.75 | 66.0625 | 0
2022 | 56403300 | 3 | March | LMSB-MD | 14 | 1.25 | 15.25 | 528.5 | 63.85
2022 | 56403300 | 3 | March | LMSB-OD | 3 | 0 | 3 | 113.25 | 0
2022 | 56403300 | 3 | March | LMSB-PD | 26.75 | 15.25 | 42 | 1009.8125 | 778.97
2022 | 56403300 | 3 | March | LMSB-SD | 13.5 | 8 | 21.5 | 509.625 | 408.64
2022 | 56403300 | 3 | March | LMSB-TB | 12 | 2.25 | 14.25 | 453 | 114.93
2022 | 56403300 | 3 | March | LMSB-TM | 22 | 7.5 | 29.5 | 830.5 | 383.1
2022 | 56403300 | 3 | March | LMSB-WD | 0.25 | 0 | 0.25 | 9.4375 | 0
2022 | 56403300 | 3 | March | LMSB-YW | 6 | 4.25 | 10.25 | 226.5 | 217.09

## ALLCPH
Year | Month | MonthN | ST Hours | OT Hours | TotalHours | Cost | CostPH | ClientID | Year | Month | MonthN | IT | II SQFT | Hours | Total SQF | ClientID | SQFPH | Year | Month | MonthN | ST Hours | OT Hours | TotalHours | Cost | CostPH | ClientID
2022 | 1 | January | 20 | 0 | 20 | 878.64 | 43.932 | 56403200 | 2022 | 3 | March | Fiber Glass | 910.0147 | 24 | 910.0147 | 56403200 | 138.05 | 2022 | 1 | January | 6 | 0 | 6 | 303.94 | 50.6567 | 56403200
2022 | 1 | January | 76 | 7 | 83 | 3609.52 | 43.4882 | 56403300 | 2022 | 3 | March | Pyrogel | 917.6723 | 46 | 917.6723 | 56403200 | 356.92 | 2022 | 1 | January | 10 | 2 | 12 | 679.34 | 56.6117 | 56403300
2022 | 2 | February | 642.5 | 35 | 677.5 | 29481.07 | 43.5145 | 56403200 | 2022 | 3 | March | Pyrogel | 1270.7742 | 63 | 1270.7742 | 56403300 | 302.81 | 2022 | 2 | February | 125 | 10 | 135 | 7047.87 | 52.2064 | 56403200
2022 | 2 | February | 1267 | 578 | 1845 | 87115.74 | 47.2172 | 56403300 | 2022 | 3 | March | Fiber Glass | 198.9675 | 15 | 198.9675 | 56403300 | 83.26 | 2022 | 2 | February | 195 | 123.5 | 318.5 | 19157.23 | 60.1483 | 56403300
2022 | 2 | February | 0 | 30 | 30 | 1764.42 | 58.814 | 56500300 | [9 empty] | 2022 | 2 | February | 0 | 6 | 6 | 456.24 | 76.04 | 56500300
2022 | 3 | March | 230.5 | 0 | 230.5 | 9724.69 | 42.1895 | 56403200 | [9 empty] | 2022 | 3 | March | 36 | 0 | 36 | 1808.12 | 50.2256 | 56403200
2022 | 3 | March | 1113.5 | 498 | 1611.5 | 76014.66 | 47.1701 | 56403300 | [9 empty] | 2022 | 3 | March | 188 | 96 | 284 | 16737.8 | 58.9359 | 56403300

## ALLHours
Year | ClientID | Month | MonthN | TotalHours | ST | OT | Year | ClientID | Month | MonthN | TotalHours | ST | OT | Travelers | Locals | Year | Month | Hours | Days | MonthN
2022 | 56403200 | 2 | February | 542.5 | 517.5 | 25 | 2022 | 56403200 | 1 | January | 20 | 20 | 0 | 7 | 0 | 2022 | March | 8 | 1 | 3
2022 | 56403200 | 1 | January | 14 | 14 | 0 | 2022 | 56403200 | 2 | February | 677.5 | 642.5 | 35 | 0 | 9
2022 | 56403200 | 3 | March | 194.5 | 194.5 | 0 | 2022 | 56403200 | 3 | March | 230.5 | 230.5 | 0
2022 | 56403300 | 2 | February | 1526.5 | 1072 | 454.5 | 2022 | 56403300 | 1 | January | 83 | 76 | 7
2022 | 56403300 | 1 | January | 71 | 66 | 5 | 2022 | 56403300 | 2 | February | 1845 | 1267 | 578
2022 | 56403300 | 3 | March | 1327.5 | 925.5 | 402 | 2022 | 56403300 | 3 | March | 1611.5 | 1113.5 | 498
2022 | 56500300 | 2 | February | 24 | 0 | 24 | 2022 | 56500300 | 2 | February | 30 | 0 | 30

## CostHPTAS
Year | PO | Weekly | ClientID | ST Hours | OT Hours | OT Cost | ST Cost | Total Exp | Total Mat
2022 | 4404165949 | 2022-02-13 | 56213200 | 40 | 0 | 0 | 1311.2 | 0 | 0
2022 | 4404165949 | 2022-02-20 | 56213200 | 40 | 0 | 0 | 1311.2 | 0 | 0
2022 | 4404165949 | 2022-02-27 | 56213200 | 40 | 0 | 0 | 1311.2 | 0 | 0
2022 | 4404165949 | 2022-03-06 | 56213200 | 24 | 0 | 0 | 786.72 | 0 | 0
2022 | 56403200 | 2022-02-06 | 56403200 | 0 | 2 | 102.16 | 0 | 0 | 0
2022 | 4501160154 | 2022-02-20 | 56403200 | 0 | 0 | 0 | 0 | 0 | 0
2022 | 4501160154 | 2022-02-27 | 56403200 | 0 | 0 | 0 | 0 | 0 | 0
2022 | 4501160155 | 2022-02-27 | 56403200 | 0 | 0 | 0 | 0 | 0 | 0
2022 | 4501160156 | 2022-02-20 | 56403200 | 0 | 0 | 0 | 0 | 0 | 0
2022 | 4501160317 | 2022-02-06 | 56403200 | 36.5 | 0 | 0 | 1570.01 | 0 | 0
2022 | 4501160317 | 2022-02-13 | 56403200 | 26 | 0 | 0 | 1107.46 | 0 | 130
2022 | 4501160317 | 2022-02-20 | 56403200 | 36 | 0 | 0 | 1563.52 | 0 | 0
2022 | 4501160317 | 2022-02-27 | 56403200 | 22 | 0 | 0 | 936.8 | 0 | 0
2022 | 4501160317 | 2022-03-06 | 56403200 | 4 | 0 | 0 | 164.2 | 0 | 0
2022 | 4501160317 | 2022-03-13 | 56403200 | 76.5 | 0 | 0 | 3226.05 | 0 | 0
2022 | 4501160317 | 2022-03-20 | 56403200 | 38 | 0 | 0 | 1600.06 | 0 | 0
2022 | 4501160318 | 2022-02-06 | 56403200 | 56 | 0 | 0 | 2376.52 | 0 | 0
2022 | 4501160318 | 2022-02-20 | 56403200 | 38 | 22 | 1317.8 | 1617.54 | 0 | 0
2022 | 4501160318 | 2022-03-06 | 56403200 | 4.5 | 0 | 0 | 179.78 | 0 | 0
2022 | 4501160318 | 2022-02-27 | 56403200 | 43 | 1 | 55.65 | 1831.07 | 0 | 0
2022 | 4501160319 | 2022-02-06 | 56403200 | 11 | 0 | 0 | 495.15 | 0 | 0
2022 | 4501160319 | 2022-02-13 | 56403200 | 132.5 | 0 | 0 | 5641.8 | 0 | 0
2022 | 4501160319 | 2022-02-20 | 56403200 | 20 | 6 | 353.56 | 838.2 | 0 | 0
2022 | 4501160319 | 2022-03-06 | 56403200 | 82 | 0 | 0 | 3457.44 | 0 | 0
2022 | 4501160319 | 2022-02-27 | 56403200 | 58 | 0 | 0 | 2466.62 | 0 | 0
2022 | 4501160320 | 2022-02-06 | 56403200 | 52 | 0 | 0 | 2198.06 | 0 | 0
2022 | 4501160320 | 2022-02-13 | 56403200 | 21 | 6 | 374.68 | 905.65 | 0 | 0
2022 | 4501160320 | 2022-02-20 | 56403200 | 71 | 0 | 0 | 3059.39 | 0 | 0
2022 | 4501160320 | 2022-02-27 | 56403200 | 23.5 | 0 | 0 | 993.42 | 0 | 430
2022 | 4501160320 | 2022-03-06 | 56403200 | 9.5 | 0 | 0 | 395.76 | 0 | 0
2022 | 4501160320 | 2022-03-13 | 56403200 | 8 | 0 | 0 | 342.44 | 0 | 0
2022 | 4501160320 | 2022-03-20 | 56403200 | 24 | 0 | 0 | 1015.77 | 0 | 0
2022 | 4501147751 | 2022-03-20 | 56403300 | 0 | 0 | 0 | 0 | 20 | 0
2022 | 4501160157 | 2022-02-27 | 56403300 | 0 | 0 | 0 | 0 | 0 | 0
2022 | 4501160317 | 2022-02-20 | 56403300 | 205 | 24 | 1408.71 | 8541.91 | 0 | 0
2022 | 4501160317 | 2022-02-13 | 56403300 | 19 | 193 | 11083.41 | 807.05 | 0 | 0
2022 | 4501160317 | 2022-02-06 | 56403300 | 47.5 | 26 | 1534.78 | 2022.23 | 0 | 91
2022 | 4501160317 | 2022-03-20 | 56403300 | 87 | 136 | 7902.96 | 3724.3 | 50 | 0
2022 | 4501160317 | 2022-04-17 | 56403300 | 0 | 0 | 0 | 0 | 0 | 136.5
2022 | 4501160317 | 2022-03-13 | 56403300 | 173 | 16 | 1023.26 | 7329.83 | 0 | 0
2022 | 4501160317 | 2022-03-06 | 56403300 | 121.5 | 38 | 2266.45 | 5158.42 | 0 | 0
2022 | 4501160317 | 2022-02-27 | 56403300 | 95.5 | 171 | 9924.47 | 4050.48 | 0 | 0
2022 | 4501160318 | 2022-03-06 | 56403300 | 118 | 2 | 111.3 | 4947.35 | 0 | 0
2022 | 4501160318 | 2022-03-13 | 56403300 | 120 | 154 | 8740.15 | 5068.94 | 0 | 100
2022 | 4501160318 | 2022-03-20 | 56403300 | 248 | 114 | 6598.83 | 10427.6 | 15 | 0
2022 | 4501160318 | 2022-02-20 | 56403300 | 76 | 7 | 446.15 | 3281.84 | 0 | 0
2022 | 4501160318 | 2022-02-06 | 56403300 | 86 | 14 | 881.01 | 3662.96 | 0 | 0
2022 | 4501160318 | 2022-02-13 | 56403300 | 138.5 | 17 | 993.47 | 5825.42 | 0 | 0
2022 | 4501160318 | 2022-02-27 | 56403300 | 144.5 | 22 | 1287.58 | 6127.5 | 0 | 0
2022 | 4501160319 | 2022-02-06 | 56403300 | 75 | 37 | 2119.14 | 3166.55 | 0 | 0
2022 | 4501160319 | 2022-02-20 | 56403300 | 29 | 0 | 0 | 1204.35 | 0 | 0
2022 | 4501160319 | 2022-02-13 | 56403300 | 52.5 | 0 | 0 | 2242.33 | 0 | 0
2022 | 4501160319 | 2022-02-27 | 56403300 | 52 | 0 | 0 | 2154.12 | 0 | 0
2022 | 4501160319 | 2022-03-06 | 56403300 | 93 | 0 | 0 | 3967.16 | 0 | 0
2022 | 4501160319 | 2022-03-13 | 56403300 | 80.5 | 38 | 2200.48 | 3403.82 | 0 | 0
2022 | 4501160319 | 2022-03-20 | 56403300 | 61 | 0 | 0 | 2598.55 | 0 | 0
2022 | 4501160320 | 2022-02-06 | 56403300 | 105.5 | 5 | 308.47 | 4415.9 | 0 | 0
2022 | 4501160320 | 2022-03-20 | 56403300 | 22 | 0 | 0 | 945.72 | 0 | 0
2022 | 4501160320 | 2022-03-13 | 56403300 | 22 | 0 | 0 | 946.7 | 0 | 0
2022 | 4501160320 | 2022-03-06 | 56403300 | 55.5 | 6 | 379.94 | 2284.29 | 0 | 0
2022 | 4501160320 | 2022-02-27 | 56403300 | 41.5 | 34 | 2024.19 | 1751.99 | 0 | 0
2022 | 4501160320 | 2022-02-20 | 56403300 | 5 | 16 | 937.13 | 205.25 | 0 | 0
2022 | 4501160320 | 2022-02-13 | 56403300 | 90.5 | 13 | 765.61 | 3782.29 | 0 | 0
2022 | 56403600 | 2022-03-13 | 56403600 | 0 | 48 | 2100.96 | 0 | 0 | 0
2022 | 4404591689 | 2022-03-06 | 56500300 | 0 | 30 | 1764.42 | 0 | 0 | 0

## Scaffold
Labor WO / Network # | TYPE (O,M,T,C) | Tag # | STFOREMAN | Pieces | Unit | Location | Date UP | ACTIVEDAYS | SRL's | M-Rent | Lat | Long
3348495 | M | 1145 | Jibran Rios | 35 | P1TICL Refrigeration | P1TICL Refrigeration | 01/06/2022 | 254 | 0 | 0.64 | 41.8783 | -87.6243
3348628 | M | 1143 | Jibran Rios | 3 | P1FIN A Micronizing | P1FIN A Micronizing | 01/04/2022 | 256 | 0 | 0.12 | 41.8783 | -87.6243
3348700 | M | 1146 | Jibran Rios | 5 | P2TICL Purification | P2TICL Purification | 01/07/2022 | 253 | 0 | 0.1 | 41.8783 | -87.6243
3348700 | M | 1147 | ERICK MORFIN | 7 | P1TICL Purification | Purification | 03/21/2022 | 180 | 0 | 0.04 | 41.8783 | -87.6243
3349518 | M | 1140 | Jibran Rios | 18 | P1TICL Chlorination | P1TICL Chlorination | 03/01/2022 | 200 | 0 | 9.3 | 41.8783 | -87.6243
3349518 | M | 1141 | Jibran Rios | 12 | P1TICL Chlorination | P1TICL Chlorination | 01/04/2022 | 256 | 0 | 9.17 | 41.8783 | -87.6243
3349518 | M | 1142 | Jibran Rios | 3 | P1TICL Chlorination | P1TICL Chlorination | 01/04/2022 | 256 | 0 | 0.09 | 41.8783 | -87.6243
3349518 | M | 1148 | Jibran Rios | 28 | P1TICL Chlorination | P1TICL Chlorination | 03/01/2022 | 200 | 0 | 0.57 | 0 | 0
4404165949 | T | 2000 | JIBRAN RIOS | 6 | P1TICL B Fume | P1TICL B Fume | 01/11/2022 | 249 | 0 | 0 | 41.8783 | -87.6243

## ScaBTools
Year | MONTHB | STWRKHRS | STMTRLHRS | STTRVL | STWTRHRS | STALRMHRS | STSFTYHRS | STSTDBYHRS | OTHERHRS | STHRS | Task | MTMBQY | MONTH | Tools B Pieces
2022 | January | 9 | 2 | 7 | 0 | 0 | 6 | 0 | 6 | 30 | Build | 55 | 1 | 6.1111
2022 | March | 6 | 2 | 3 | 1 | 0.5 | 3 | 0 | 2 | 17.5 | Build | 58 | 3 | 9.6667

## ScaDTools
Year | MONTHD | DHWRKHRS | DHMTRLHRS | DHTRVL | DHWTRHRS | DHALRMHRS | DHSFTYHRS | DHSTDBYHRS | OTHERHRS | DHRS | Task | MTMBQY | MONTH | Tools D Pieces
2022 | January | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 5 | Dism | 8 | 1 | 4
2022 | March | 24 | 4 | 3 | 0 | 0 | 0 | 0 | 3.5 | 34.5 | Dism | 8 | 3 | 0.33333

## ScaMTools
Year | MONTHM | MHWRKHRS | MHMTRLHRS | MHTRVL | MHWTRHRS | MHALRMHRS | MHSFTYHRS | MHSTDBYHRS | OTHERHRS | MHRS | Task | MTQTY | MONTH | Tools M Pieces
2022 | 1 | 18 | 7 | 1.5 | 0 | 0 | 6 | 0 | 0 | 32.5 | Mod | 0 | January | 0
2022 | 3 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 5 | Mod | 0 | March | 0

## ACM
Year | Month | MonthN | IT | II SQFT | Hours | Total SQF | ClientID | SQFPH
2022 | 3 | March | Asbestos | 135.8739 | 23 | 135.8739 | 56403300 | 52.01
2022 | 3 | March | Asbestos | 341.3864 | 36 | 341.3864 | 56403200 | 55.53

## AR Invoices
ClientID | PO | Invoice# | Amount | Invoice Date | Due Date | Past Due Days
56403200 | 4501160317 | 1116 | 164.2 | 03/06/2022 | 03/06/2022 | 194
56403200 | 4501160318 | 1117 | 179.775 | 03/06/2022 | 03/06/2022 | 194
56403200 | 4501160319 | 1118 | 3457.44 | 03/06/2022 | 03/06/2022 | 194
56403200 | 4501160320 | 1119 | 395.765 | 03/06/2022 | 03/06/2022 | 194
56403300 | 4501160317 | 1116 | 7424.875 | 03/06/2022 | 03/06/2022 | 194
56403300 | 4501160318 | 1117 | 5058.65 | 03/06/2022 | 03/06/2022 | 194
56403300 | 4501160319 | 1118 | 3967.16 | 03/06/2022 | 03/06/2022 | 194
56403300 | 4501160320 | 1119 | 2664.225 | 03/06/2022 | 03/06/2022 | 194

## Invoices
ClientID | Pay Terms | PO | Invoice | Invoice Date | Total Hours PO | Total Labor | Total Expenses | Total PerDiem | 3rdParty | ScRent | CoEQ | Material | Subcontractors | Other | ExtraCostMaterial | Total Material | Total Cost
56403200 | 0 | 4501160317 | 1116 | 03/06/2022 | 4 | 164.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164.2
56403200 | 0 | 4501160318 | 1117 | 03/06/2022 | 4.5 | 179.775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179.775
56403200 | 0 | 4501160319 | 1118 | 03/06/2022 | 82 | 3457.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3457.44
56403200 | 0 | 4501160320 | 1119 | 03/06/2022 | 9.5 | 395.765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395.765
56403300 | 0 | 4501160317 | 1116 | 03/06/2022 | 159.5 | 7424.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7424.875
56403300 | 0 | 4501160318 | 1117 | 03/06/2022 | 120 | 5058.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5058.65
56403300 | 0 | 4501160319 | 1118 | 03/06/2022 | 93 | 3967.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3967.16
56403300 | 0 | 4501160320 | 1119 | 03/06/2022 | 61.5 | 2664.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2664.225

## ClientID
ClientID | Company Name | Client Name
56213200 | LyondellBasell | Ted Cudak C
56403200 | INEOS | Danny Moore M
56403300 | INEOS | Danny Moore M
56403600 | INEOS | Danny Moore M
56500300 | INEOS | Danny Moore M